## Program Overview
Program | IIPS Production Market Data & Intelligence Ingestion Program v1.0
Version | v1.0 — Requirements / Development Roadmap
Status | PLANNING SPECIFICATION — NOT AN IMPLEMENTATION AUTHORIZATION
Date | 2026-09-08
Scope | Full data-plane + engine/evidence/API + all existing applicable UI surfaces + visual parity + E2E + production activation/operations
UI scope | All existing IIPS UI surfaces; applicability marked per work item
Data domains | Market prices/quotes; OHLCV; fundamentals; corporate actions; instrument master; news/events; estimates; macro; alternative data; exchange/reference metadata
Provider strategy | Provider-agnostic replaceable adapters
Development strategy | Deterministic/local fixtures first; production adapters later
Operating modes | LIVE; SNAPSHOT; HISTORICAL/POINT-IN-TIME
Production boundary | Licensing, credentials and activation are separate later gates
Certification | Phase-by-phase development → validation → certification
Target | Functional parity with supplied IIPS screenshot, not visual similarity alone
Recommended Git Repository | iips-production-market-data
Recommended Windows Workspace | G:\IIPS-Production-Market-Data
Repository Strategy | NEW dedicated repository; keep production market-data plane separate from the existing IIPS E2E/platform repository.
Integration Model | One integrated IIPS product; separate repository engineering boundaries.
Existing IIPS Repository | Remains the existing product/platform repository; no forced merge.
New Data Repository | iips-production-market-data
Integration Boundary | Stable/governed/certified contracts and APIs between the data plane and existing IIPS product.
Repository vs Runtime | Repository separation does not prescribe deployment topology.
Reuse Rule | REUSE / ADAPT / EXTEND / NEW classification before implementation.
Architecture Change Rule | No silent rewrite; genuine conflicts require explicit authority/ADR.
P01 Entry Prerequisite | Existing IIPS → New Data Program Integration/Reuse Baseline reconciled.

## IIPS Integration Baseline
Integration ID | Existing IIPS Capability / Surface | New Program Touchpoint | Treatment | Expected Integration Boundary | Entry Evidence / Source | Validation Required | Authority / Gate | Status | Notes | Repository Boundary | Runtime Integration Note
INT-001 | Certified IIPS architecture / platform contracts | P01 Data Contract & Canonical Domain Model | REUSE / PRESERVE | New canonical data contracts must map to existing certified interfaces; no architecture rewrite. | Existing IIPS certified baseline; new program spec/tracker | Contract compatibility and regression verification | P00/P01 | BASELINE — VERIFY | Confirm exact interfaces during discovery. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-002 | Existing Engine / methodology execution | P11 Engine / Research / Evidence Integration | REUSE / ADAPT | Production data becomes an upstream governed input; existing methodology authority remains authoritative unless separately changed. | Existing certified engine/methodology artifacts | Deterministic input/output and provenance tests | P11 | BASELINE — VERIFY | Do not redesign scoring/methodology in this program. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-003 | Existing evidence / provenance / replay mechanisms | P11 + P12 | REUSE / EXTEND ONLY WHERE REQUIRED | Production data must carry source, timestamp, freshness, lineage and reproducibility metadata through existing evidence mechanisms. | Existing evidence/replay certification; new data requirements | Lineage, provenance, replay/PIT tests | P11/P15 | BASELINE — VERIFY | Extension requires explicit contract evidence. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-004 | Existing G2 / DTO / product API contracts | P12 Certified Data APIs / G2 Product Contracts | REUSE / ADAPT | Expose new production-data capabilities through stable governed contracts; avoid UI coupling to providers. | Existing G2/API certification baseline | Schema/contract compatibility + regression | P12 | BASELINE — VERIFY | Provider identity should remain behind the data-plane abstraction. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-005 | Dashboard | P13 Product UI Data Integration | REUSE UI / INTEGRATE DATA | Existing Dashboard remains the product surface; production-grade values replace deterministic/non-production inputs through certified APIs. | Existing completed IIPS UI baseline; target screenshot | Functional, data provenance, responsive/visual parity | P13-P15 | BASELINE — VERIFY | Dashboard remains a late aggregation surface. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-006 | Company Workspace | P13 | REUSE UI / INTEGRATE DATA | Company/security-master, market, fundamentals, events and evidence data consumed through governed contracts. | Existing completed IIPS product baseline | Functional + data lineage + PIT where applicable | P13-P15 | BASELINE — VERIFY | No surface rebuild unless gap is proven. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-007 | Portfolio | P13 | REUSE UI / INTEGRATE DATA | Prices, positions, risk inputs and derived intelligence consumed via governed APIs. | Existing completed IIPS product baseline | Functional + freshness + provenance | P13-P15 | BASELINE — VERIFY | Existing portfolio behavior remains the baseline. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-008 | Research | P13 | REUSE UI / INTEGRATE DATA | Fundamentals, events, estimates, macro/alternative inputs and evidence consumed through certified contracts. | Existing completed IIPS product baseline | Functional + provenance + reproducibility | P13-P15 | BASELINE — VERIFY | Research semantics remain governed. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-009 | Screener | P13 | REUSE UI / INTEGRATE DATA | Canonical market/fundamental/security-master data supplies screening. | Existing completed IIPS product baseline | Deterministic filters + freshness + data-quality propagation | P13-P15 | BASELINE — VERIFY | Provider-neutral at UI boundary. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-010 | Decision Center | P13 | REUSE UI / INTEGRATE DATA | Decision inputs/outputs consume certified engine/evidence APIs. | Existing completed IIPS product baseline | Functional + evidence + audit/provenance regression | P13-P15 | BASELINE — VERIFY | No methodology change implied. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-011 | Watchlists / Alerts | P13 | REUSE UI / INTEGRATE DATA | Market/event changes and alert inputs consume validated canonical data. | Existing completed IIPS product baseline | Event/freshness/threshold tests | P13-P15 | BASELINE — VERIFY | Operational event semantics require data-quality controls. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-012 | Reports | P13 | REUSE UI / INTEGRATE DATA | Reports consume reproducible historical/PIT and evidence-backed data. | Existing completed IIPS product baseline | Historical/PIT reproducibility tests | P13-P15 | BASELINE — VERIFY | Point-in-time correctness is mandatory where applicable. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-013 | Collaboration | P13 | REUSE UI / INTEGRATE DATA | Collaboration references governed IIPS objects/evidence rather than raw provider records. | Existing completed IIPS product baseline | Object/reference integrity tests | P13-P15 | BASELINE — VERIFY | No direct provider coupling. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-014 | Administration / Settings | P03 + P16/P17 | REUSE UI / EXTEND | Expose only approved operational/provider/entitlement controls through governed admin boundaries. | Existing administration baseline + new entitlement/security requirements | Authorization, tenant isolation, audit tests | P03/P16/P17 | BASELINE — VERIFY | Production activation remains separately authorized. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-015 | Global Search / Command Palette | P04 + P13 | REUSE UI / INTEGRATE DATA | Security master and governed product objects provide search/navigation targets. | Existing completed IIPS product baseline | Search identity and object resolution tests | P04/P13-P15 | BASELINE — VERIFY | No raw-provider search surface. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-016 | Existing E2E/certification suites | P15 Full E2E Certification | REUSE / REGRESSION | New data-plane integration must preserve existing certified behavior while adding production-data qualification. | Existing E2E certification baseline | Full regression + new data-plane suites | P15 | BASELINE — VERIFY | Existing certifications are not reopened unless a contract/regression failure requires it. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-017 | Existing target/reference screenshot | P14 UX / Visual Parity | REFERENCE / PRESERVE | Screenshot defines target product surface coverage; it does not authorize a visual-only rebuild. | Existing target screenshot | Functional parity + accessibility/responsive/visual checks | P14/P15 | BASELINE — VERIFY | Functional parity takes precedence over pixel similarity. | Separate repos; integrated product | Integration through governed contracts/APIs; runtime topology remains a later governed decision.
INT-018 | Production activation boundary | P16 Production Provider Onboarding & Activation | NEW GATED BOUNDARY | Production credentials, licensing, provider activation and live operation are separate from development certification. | New program scope decision | Licensing, secrets, connectivity, reconciliation, operational readiness | P16 | NOT AUTHORIZED YET | No production activation is implied by P00-P15 completion. | Separate repos; gated production boundary | Production activation is separate authorization; repo split does not imply separate end-user product.
Integration Principle | The existing completed IIPS product is the consuming/product platform. This program operationalizes the governed data plane behind it; it is not a second UI/product rebuild or an architecture rewrite.
P01 prerequisite | Before P01 implementation, reconcile exact existing certified contracts, engines, evidence/provenance, DTO/G2 APIs, UI surfaces, fixtures and certification boundaries into the integration map.
Change control | Any architecture or methodology change discovered during integration requires its own explicit authority/ADR; it is not silently introduced by this program.

## Integration Decisions
Decision | Approved Position | Implication
Repository strategy | NEW dedicated repo: iips-production-market-data | Keep data-plane implementation isolated from existing certified IIPS product/platform.
Product identity | ONE integrated IIPS product | New repo is not a second product.
Integration mechanism | Stable governed/certified contracts and APIs | Data provider details remain behind the data-plane boundary.
Runtime topology | NOT PRESCRIBED by repository split | Deployment architecture is decided later from operational evidence.
Reuse policy | REUSE / ADAPT / EXTEND / NEW | Existing certified capability is the baseline; rebuild only where a gap is demonstrated.
Architecture changes | Explicit authority/ADR required | No silent architecture rewrite through this program.
P01 prerequisite | Integration/Reuse Baseline first | P01 implementation waits until existing IIPS boundaries are reconciled.

## Phase Roadmap
Phase | Name | Objective | Dependencies | Next | Integration Baseline Prerequisite
P00 | Program Baseline & Governance | Establish scope, baseline, contracts, ownership, certification model and non-goals before implementation. | None | P01–P17 | Inherited from P01 integration/reuse map.
P01 | Data Contract & Canonical Domain Model | Define canonical schemas, identifiers, timestamps, units, currencies, source/provenance and operating modes. | P00 | P02–P12 | YES — reconcile existing certified IIPS contracts/capabilities before implementation.
P02 | Provider Abstraction & Entitlement Model | Create provider-neutral adapter contracts and explicit licensing/entitlement boundaries. | P00,P01 | P03,P05,P16 | Use the P01 integration/reuse map; preserve certified boundaries.
P03 | Secrets, Security & Tenant Controls | Secure provider credentials, service identities, tenant isolation and access controls. | P00,P02 | P05,P11,P16 | Use the P01 integration/reuse map; preserve certified boundaries.
P04 | Instrument / Security Master | Establish authoritative instrument identity, mappings, listings, exchanges, currencies and lifecycle state. | P01,P02,P03 | P05–P12 | Inherited from P01 integration/reuse map.
P05 | Market Data Acquisition & Ingestion | Implement deterministic/local ingestion first, then provider adapters for quotes, prices and historical market data. | P01–P04 | P06–P12 | Inherited from P01 integration/reuse map.
P06 | Normalization & Canonical Data Pipeline | Normalize provider-specific payloads into governed canonical representations without feeding raw provider data directly to engines. | P01,P04,P05 | P07–P12 | Inherited from P01 integration/reuse map.
P07 | Data Quality, Freshness & Reconciliation | Detect missing, stale, malformed, contradictory and out-of-order data; expose quality state and reconciliation evidence. | P04–P06 | P08–P15 | Inherited from P01 integration/reuse map.
P08 | Historical / Point-in-Time & Corporate Actions | Support historical and PIT semantics, adjusted/unadjusted series, effective dates and corporate-action lineage. | P04–P07 | P09–P15 | Inherited from P01 integration/reuse map.
P09 | Fundamentals & Financial Intelligence | Ingest and normalize financial statements, ratios, valuation inputs and related fundamental datasets. | P04–P08 | P10–P15 | Inherited from P01 integration/reuse map.
P10 | News, Events, Estimates & Macro/Alternative Data | Establish governed ingestion for news/events, consensus estimates, macro and approved alternative datasets. | P04–P08 | P11–P15 | Inherited from P01 integration/reuse map.
P11 | Engine / Research / Evidence Integration | Connect canonical data to existing engines and research flows with provenance, reproducibility and evidence lineage. | P06–P10 | P12–P15 | Use the P01 integration/reuse map; preserve certified boundaries.
P12 | Certified Data APIs / G2 Product Contracts | Expose governed data through stable APIs/contracts with live, snapshot and PIT semantics. | P06–P11 | P13–P15 | Use the P01 integration/reuse map; preserve certified boundaries.
P13 | Product UI Data Integration | Make all applicable existing UI surfaces consume governed data; retain non-data surfaces as baseline where applicable. | P07–P12 | P14,P15 | Use the P01 integration/reuse map; preserve certified boundaries.
P14 | UX, Accessibility, Responsive & Visual Parity | Harden UX and qualify against the supplied screenshot target, including browser/visual validation where environment permits. | P13 | P15 | Use the P01 integration/reuse map; preserve certified boundaries.
P15 | Full E2E Certification & Functional Parity | Certify provider-to-UI data lineage, engine outputs, evidence, degraded states and screenshot functional parity. | P07–P14 | P16,P17 | Use the P01 integration/reuse map; preserve certified boundaries.
P16 | Production Provider Onboarding & Activation | Complete licensing, credentials, production connectivity, entitlement validation and controlled activation. | P02,P03,P05,P07,P15 | P17 | Use the P01 integration/reuse map; preserve certified boundaries.
P17 | Operations, Monitoring & Release Certification | Operationalize monitoring, incident handling, provider failover/staleness controls, release evidence and production certification. | P15,P16 | None | Use the P01 integration/reuse map; preserve certified boundaries.

## Work Tracker
Work ID | Phase | Area | Work Item | Requirement | Deliverable | Dependencies | Dependency Type | Entry Criteria | Exit Criteria | Test / Validation | Evidence | Authority / Gate | Status | Owner | Priority | Notes | Execution Wave | Parallel Workstream | Critical Path | Parallel With | Parallelization Notes
P00-01 | P00 | Governance | Program charter | Define scope, objective, non-goals, lifecycle and success criteria. | Approved program charter | None | None | Program authority decision exists | Charter baselined | Document review | Charter + decision record | Phase gate | NOT STARTED |  | High |  | W0 | WS-A Governance & Contracts | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P00-02 | P00 | Governance | Baseline reconciliation | Reconcile current certified platform/product baseline against this program. | Baseline matrix | None | None | Current certification records available | Baseline and gaps recorded | Traceability review | Baseline reconciliation | Phase gate | NOT STARTED |  | High |  | W0 | WS-A Governance & Contracts | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P00-03 | P00 | Governance | Certification model | Define phase gates, evidence rules, concessions and stop conditions. | Certification framework | P00-01 | Sequential | Charter baselined | Gate model approved | Governance review | Certification template | Phase gate | NOT STARTED |  | High |  | W0 | WS-A Governance & Contracts | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P00-04 | P00 | Governance | Release boundary | Separate planning scope from implementation/production authorization. | Release/authority matrix | P00-01 | Governance | Charter baselined | Authorization boundaries explicit | Authority review | Authority matrix | Phase gate | NOT STARTED |  | High |  | W0 | WS-A Governance & Contracts | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P01-01 | P01 | Contracts | Canonical identifiers | Define instrument/company/portfolio/research/event identifiers and cross-provider mapping semantics. | Canonical ID specification | P00-02 | Hard | Baseline reconciled | IDs versioned and testable | Contract tests | ID contract + fixtures | Phase gate | NOT STARTED |  | High |  | W1 | WS-A Governance & Contracts | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P01-02 | P01 | Contracts | Timestamp/as-of semantics | Define event time, received time, publication time, effective time and as-of semantics. | Time semantics specification | P00-02 | Hard | Baseline reconciled | All domains mapped to time semantics | Contract tests | Time contract | Phase gate | NOT STARTED |  | High |  | W1 | WS-A Governance & Contracts | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P01-03 | P01 | Contracts | Units/currency/adjustment rules | Define units, currencies, precision, scaling and adjustment semantics. | Measurement contract | P01-01 | Hard | ID contract drafted | Canonical measurements deterministic | Golden fixtures | Measurement fixtures | Phase gate | NOT STARTED |  | High |  | W1 | WS-A Governance & Contracts | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P01-04 | P01 | Contracts | LIVE/SNAPSHOT/PIT modes | Define explicit mode behavior and prohibition on accidental mode mixing. | Operating mode contract | P01-02 | Hard | Time semantics defined | Mode rules testable | Contract tests | Mode contract | Phase gate | NOT STARTED |  | High |  | W1 | WS-A Governance & Contracts | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P01-05 | P01 | Contracts | Provenance schema | Define provider/source/dataset/version/received-at/as-of lineage fields. | Provenance contract | P01-01,P01-02 | Hard | Canonical IDs/time defined | Every governed datum traceable | Schema + lineage tests | Provenance fixtures | Phase gate | NOT STARTED |  | High |  | W1 | WS-A Governance & Contracts | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P02-01 | P02 | Providers | Provider adapter interface | Create replaceable provider-neutral adapter contract. | Provider SPI/interface | P01-01,P01-05 | Hard | Canonical contract exists | Two implementations can conform | Contract test suite | Provider adapter contract | Phase gate | NOT STARTED |  | High |  | W1 | WS-A Governance & Contracts | NO | P03 (discovery/prep) | Provider abstraction can be designed while security/entitlement controls are prepared; phase certification still respects dependencies.
P02-02 | P02 | Providers | Entitlement/licensing model | Represent dataset entitlements, usage restrictions and environment eligibility. | Entitlement model | P00-04,P02-01 | Governance | Authority boundary defined | Activation can verify entitlement | Review + negative tests | Entitlement matrix | Phase gate | NOT STARTED |  | High |  | W1 | WS-A Governance & Contracts | NO | P03 (discovery/prep) | Provider abstraction can be designed while security/entitlement controls are prepared; phase certification still respects dependencies.
P02-03 | P02 | Providers | Provider selection criteria | Define quality, coverage, latency, licensing, cost and fallback criteria. | Provider evaluation rubric | P02-01 | Soft | Adapter model exists | Provider candidates can be compared | Review | Provider rubric | Phase gate | NOT STARTED |  | High |  | W1 | WS-A Governance & Contracts | NO | P03 (discovery/prep) | Provider abstraction can be designed while security/entitlement controls are prepared; phase certification still respects dependencies.
P03-01 | P03 | Security | Credential/secrets handling | Secure provider credentials and prohibit secrets in code/tests/logs. | Secrets design | P02-01 | Hard | Provider interface exists | Secrets flow passes security checks | Security tests | Security evidence | Phase gate | NOT STARTED |  | High |  | W1 | WS-A Governance & Contracts | NO | P02 (discovery/prep) | Security, secrets, tenant-control design can proceed alongside provider-abstraction discovery; implementation certification remains dependency-controlled.
P03-02 | P03 | Security | Tenant/access controls | Enforce tenant and role boundaries for data access. | Access-control contract | P01-05,P03-01 | Hard | Provenance model exists | Unauthorized access denied | Authz tests | Access-control evidence | Phase gate | NOT STARTED |  | High |  | W1 | WS-A Governance & Contracts | NO | P02 (discovery/prep) | Security, secrets, tenant-control design can proceed alongside provider-abstraction discovery; implementation certification remains dependency-controlled.
P04-01 | P04 | Security Master | Instrument master | Canonical instrument registry with symbol/ISIN/exchange/currency/lifecycle fields. | Instrument master service/model | P01,P02,P03 | Hard | Contracts stable | Deterministic identity resolution | Golden mapping tests | Instrument fixtures | Phase gate | NOT STARTED |  | High |  | W2 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P04-02 | P04 | Security Master | Provider symbol mappings | Map provider-specific identifiers to canonical instruments. | Mapping tables/service | P04-01 | Hard | Master exists | All supported providers resolve mappings | Mapping reconciliation | Mapping evidence | Phase gate | NOT STARTED |  | High |  | W2 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P04-03 | P04 | Security Master | Lifecycle/reference metadata | Handle listings, delistings, exchange metadata and instrument state. | Lifecycle/reference model | P04-01 | Hard | Master exists | Historical lifecycle reproducible | Scenario tests | Lifecycle fixtures | Phase gate | NOT STARTED |  | High |  | W2 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P05-01 | P05 | Ingestion | Local deterministic market feed | Build deterministic local provider for development/certification. | Local market adapter | P02-01,P04-01 | Hard | Provider contract + master | Repeatable fixture ingestion | Repeat-run tests | Fixture dataset | Phase gate | NOT STARTED |  | High |  | W3 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P05-02 | P05 | Ingestion | LIVE market adapter | Implement approved live provider adapter for quotes/prices. | Live market adapter | P02-01,P02-02,P03-01,P04-02 | Hard | Entitlement + secrets ready | Authenticated ingestion works | Integration tests | Provider evidence | Phase gate | NOT STARTED |  | High |  | W3 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P05-03 | P05 | Ingestion | Historical market adapter | Ingest historical OHLCV and required depth where licensed. | Historical adapter | P05-01,P04-02 | Hard | Local adapter works | Historical load reproducible | Load/reconcile tests | Historical sample | Phase gate | NOT STARTED |  | High |  | W3 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P05-04 | P05 | Ingestion | Ingestion orchestration | Scheduling, retries, idempotency and checkpointing. | Ingestion orchestrator | P05-01,P05-02 | Hard | Adapters conform | Replay does not duplicate data | Failure/replay tests | Run logs | Phase gate | NOT STARTED |  | High |  | W3 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P06-01 | P06 | Canonical | Normalization pipeline | Convert provider payloads into canonical records. | Normalization pipeline | P01,P04,P05 | Hard | Input fixtures available | Canonical output deterministic | Golden tests | Canonical fixtures | Phase gate | NOT STARTED |  | High |  | W4 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P06-02 | P06 | Canonical | Raw/canonical separation | Keep raw provider payloads separate from governed canonical data. | Storage boundary | P05-04,P06-01 | Hard | Pipeline exists | Raw data never bypasses validation | Architecture + negative tests | Boundary evidence | Phase gate | NOT STARTED |  | High |  | W4 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P06-03 | P06 | Canonical | Deduplication/idempotency | Prevent duplicate records across retries/replays/providers. | Deduplication rules | P06-01,P06-02 | Hard | Canonical schema stable | Repeated ingestion stable | Replay tests | Replay evidence | Phase gate | NOT STARTED |  | High |  | W4 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P07-01 | P07 | Quality | Quality rule framework | Define completeness, validity, range, continuity and reconciliation checks. | DQ rule engine | P06-01 | Hard | Canonical data exists | Rules execute and classify failures | Rule tests | DQ evidence | Phase gate | NOT STARTED |  | High |  | W5 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P07-02 | P07 | Quality | Freshness/staleness | Calculate freshness and explicit stale/unavailable states. | Freshness service | P01-02,P07-01 | Hard | Time semantics stable | Freshness state reproducible | Time/freshness tests | Freshness evidence | Phase gate | NOT STARTED |  | High |  | W5 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P07-03 | P07 | Quality | Provider reconciliation | Compare overlapping provider/reference values and resolve policy. | Reconciliation service | P02-03,P07-01 | Hard | Providers selected | Discrepancies classified | Reconciliation tests | Reconciliation reports | Phase gate | NOT STARTED |  | High |  | W5 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P07-04 | P07 | Quality | Degraded-state contract | Define behavior for missing, stale, partial and failed data. | Degraded-state contract | P07-01,P07-02 | Hard | DQ states defined | Consumers receive explicit state | Negative tests | Degraded fixtures | Phase gate | NOT STARTED |  | High |  | W5 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P08-01 | P08 | Historical/PIT | PIT storage model | Store data so prior-as-of states are reproducible. | PIT model | P01-02,P06-01 | Hard | Time semantics stable | Historical query reproducible | Backdated fixtures | PIT evidence | Phase gate | NOT STARTED |  | High |  | W6 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P08-02 | P08 | Corporate Actions | Corporate action ingestion | Dividends, splits, bonuses and other approved actions. | CA pipeline | P04-03,P05,P06 | Hard | Instrument lifecycle stable | Actions linked to instruments | Scenario tests | CA fixtures | Phase gate | NOT STARTED |  | High |  | W6 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P08-03 | P08 | Corporate Actions | Adjustment/reconciliation | Define adjusted/unadjusted series and portfolio reconciliation behavior. | Adjustment engine/rules | P08-02,P07-03 | Hard | CA data validated | Series and holdings reconcile | Golden scenarios | Adjustment evidence | Phase gate | NOT STARTED |  | High |  | W6 | WS-B Data Foundation | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P09-01 | P09 | Fundamentals | Financial statement ingestion | Ingest approved financial statement datasets with source/publication metadata. | Fundamentals pipeline | P04,P06,P08 | Hard | Canonical/PIT available | Statements reproducible by as-of | PIT tests | Fundamental fixtures | Phase gate | NOT STARTED |  | High |  | W7 | WS-C Intelligence Domains | YES | P10 | Fundamentals/financial intelligence can proceed independently of news/estimates/macro once canonical foundations are certified.
P09-02 | P09 | Fundamentals | Fundamental normalization | Map provider/accounting fields to canonical metrics and units. | Metric normalization | P09-01,P01-03 | Hard | Statements available | Canonical metrics reconcile | Golden tests | Metric mapping | Phase gate | NOT STARTED |  | High |  | W7 | WS-C Intelligence Domains | YES | P10 | Fundamentals/financial intelligence can proceed independently of news/estimates/macro once canonical foundations are certified.
P09-03 | P09 | Fundamentals | Valuation inputs | Provide governed valuation inputs used by applicable engines/UI. | Valuation data contract | P09-02,P08-01 | Hard | Metrics normalized | Inputs traceable to source | Lineage tests | Valuation evidence | Phase gate | NOT STARTED |  | High |  | W7 | WS-C Intelligence Domains | YES | P10 | Fundamentals/financial intelligence can proceed independently of news/estimates/macro once canonical foundations are certified.
P10-01 | P10 | Intelligence | News/events ingestion | Ingest approved event/news data with publication time and source lineage. | News/events pipeline | P02,P04,P06,P07 | Hard | Provider adapter ready | Events searchable/reproducible | Event tests | Event fixtures | Phase gate | NOT STARTED |  | High |  | W7 | WS-C Intelligence Domains | YES | P09 | News/events/estimates/macro/alternative-data adapters can proceed in parallel with fundamentals.
P10-02 | P10 | Intelligence | Estimates/consensus | Ingest approved estimates and consensus snapshots with PIT semantics. | Estimates pipeline | P08-01,P09-02 | Hard | PIT model ready | Prior consensus reproducible | PIT tests | Estimate fixtures | Phase gate | NOT STARTED |  | High |  | W7 | WS-C Intelligence Domains | YES | P09 | News/events/estimates/macro/alternative-data adapters can proceed in parallel with fundamentals.
P10-03 | P10 | Intelligence | Macro datasets | Ingest approved macro series with release/as-of semantics. | Macro pipeline | P08-01,P07-01 | Required by applicability | PIT + DQ ready | Macro series reproducible | Time-series tests | Macro fixtures | Phase gate | NOT STARTED |  | High |  | W7 | WS-C Intelligence Domains | YES | P09 | News/events/estimates/macro/alternative-data adapters can proceed in parallel with fundamentals.
P10-04 | P10 | Intelligence | Alternative data governance | Define approval, provenance and quality rules for alternative datasets. | Alt-data governance | P00-04,P01-05,P07-01 | Governance | Governance boundary defined | Only approved datasets admitted | Negative tests | Alt-data policy | Phase gate | NOT STARTED |  | High |  | W7 | WS-C Intelligence Domains | YES | P09 | News/events/estimates/macro/alternative-data adapters can proceed in parallel with fundamentals.
P11-01 | P11 | Engine Integration | Engine input adapters | Connect canonical data to existing certified engines without provider coupling. | Engine adapters | P06–P10 | Hard | Canonical domains certified | Engine inputs traceable | Engine integration tests | Engine lineage | Phase gate | NOT STARTED |  | High |  | W8 | WS-D Engine / Research / Evidence | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P11-02 | P11 | Engine Integration | Recalculation orchestration | Define when new data causes recalculation and how snapshots are retained. | Recalc orchestration | P07,P08,P11-01 | Hard | Engine adapters stable | Recalc deterministic | Replay tests | Recalc evidence | Phase gate | NOT STARTED |  | High |  | W8 | WS-D Engine / Research / Evidence | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P11-03 | P11 | Evidence | Evidence lineage | Attach source/as-of/engine/version to derived outputs. | Evidence integration | P01-05,P11-01 | Hard | Engine outputs available | Output lineage complete | Lineage tests | Evidence chain | Phase gate | NOT STARTED |  | High |  | W8 | WS-D Engine / Research / Evidence | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P12-01 | P12 | API | Canonical data APIs | Expose governed domain data through stable APIs. | Data API set | P06–P11 | Hard | Contracts certified | API contract tests pass | Contract/integration tests | API evidence | Phase gate | NOT STARTED |  | High |  | W9 | WS-D Engine / Research / Evidence | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P12-02 | P12 | API | G2 DTO integration | Map data and derived results to existing governed product DTO contracts. | G2 integration | P11-03,P12-01 | Hard | Evidence + APIs stable | DTOs preserve provenance/mode | DTO tests | G2 evidence | Phase gate | NOT STARTED |  | High |  | W9 | WS-D Engine / Research / Evidence | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P12-03 | P12 | API | Live/snapshot/PIT API semantics | Prevent ambiguous data mode and expose as-of/freshness explicitly. | API mode contract | P01-04,P07-02,P12-01 | Hard | Mode contract stable | Consumers cannot silently mix modes | Negative/API tests | Mode API evidence | Phase gate | NOT STARTED |  | High |  | W9 | WS-D Engine / Research / Evidence | YES | — | Phase-gate dependency controls entry/exit; no dependency bypass.
P13-01 | P13 | UI shell/data states | Global data-state framework | All applicable surfaces expose loading, empty, stale, unavailable and error states from governed contracts. | UI state components | P07-04,P12-03 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.
P13-02 | P13 | Company Workspace | Company data integration | Overview, financials, valuation, scorecard, risks, news, notes and evidence consume governed APIs. | Company integration | P09,P10,P12 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.
P13-03 | P13 | Portfolio | Portfolio integration | Holdings, allocation, performance, risk, transactions and analytics consume governed data and corporate-action semantics. | Portfolio integration | P08,P11,P12 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.
P13-04 | P13 | Research | Research integration | Research objects, company/sector/macro context and source lineage consume governed data. | Research integration | P09,P10,P11,P12 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.
P13-05 | P13 | Screener | Screener integration | Universe, filters, scores and results use canonical identifiers and current/PIT semantics. | Screener integration | P04,P11,P12 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.
P13-06 | P13 | Decision Center | Decision integration | Decisions, proposals, approvals, history and evidence display governed analytical inputs. | Decision integration | P11,P12 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.
P13-07 | P13 | Watchlists | Watchlist integration | Lists, score changes and triggers use governed data and freshness semantics. | Watchlist integration | P07,P11,P12 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.
P13-08 | P13 | Reports | Report integration | Generated reports retain source, timestamp, engine/version and evidence lineage. | Report integration | P11,P12 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.
P13-09 | P13 | Alerts | Alert integration | Rules/events/notifications expose source, event time, severity and acknowledgement state. | Alert integration | P10,P11,P12 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.
P13-10 | P13 | Collaboration | Collaboration integration | Comments, mentions, shared objects and activity retain tenant/user context. | Collaboration integration | P03,P12 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.
P13-11 | P13 | Administration | Admin integration | Provider/data configuration surfaces only expose authorized controls and auditable state. | Admin integration | P03,P12 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.
P13-12 | P13 | Settings | Settings integration | Applicable data/display preferences are governed and tenant/user scoped. | Settings integration | P03,P12 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.
P13-13 | P13 | Global Search | Search integration | Search spans company, research, holdings, decisions, evidence, alerts and reports. | Search integration | P10,P12 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.
P13-14 | P13 | Command Palette | Action integration | Quick actions operate on governed product domains and preserve authorization context. | Command integration | P03,P12 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.
P13-15 | P13 | Dashboard | Dashboard aggregation | Dashboard metrics and widgets are derived from governed domain APIs; no mock/invented metrics in certified mode. | Dashboard integration | P11,P12,P13-02..P13-09 | Hard | Applicable API contracts certified | UI consumes governed data with explicit states | UI component + integration tests | UI evidence + API lineage | Phase gate | NOT STARTED |  | High |  | W10 | WS-E Product UI | YES | Most UI surfaces except Dashboard can execute in parallel once shared contracts/state are ready | Company, Portfolio, Research, Screener, Decision Center, Watchlists, Reports, Alerts, Collaboration, Admin, Settings, Search and Command Palette can be parallelized by surface after shared product contracts; Dashboard remains the late aggregation surface.

## Dependency Matrix
Work ID | Phase | Depends On | Dependency Type | Critical? | Reason
P00-01 | P00 | None | None | YES | Program charter must be stable before dependent work can be certified.
P00-02 | P00 | None | None | YES | Baseline reconciliation must be stable before dependent work can be certified.
P00-03 | P00 | P00-01 | Sequential | YES | Certification model must be stable before dependent work can be certified.
P00-04 | P00 | P00-01 | Governance | YES | Release boundary must be stable before dependent work can be certified.
P01-01 | P01 | P00-02 | Hard | YES | Canonical identifiers must be stable before dependent work can be certified.
P01-02 | P01 | P00-02 | Hard | YES | Timestamp/as-of semantics must be stable before dependent work can be certified.
P01-03 | P01 | P01-01 | Hard | YES | Units/currency/adjustment rules must be stable before dependent work can be certified.
P01-04 | P01 | P01-02 | Hard | YES | LIVE/SNAPSHOT/PIT modes must be stable before dependent work can be certified.
P01-05 | P01 | P01-01,P01-02 | Hard | YES | Provenance schema must be stable before dependent work can be certified.
P02-01 | P02 | P01-01,P01-05 | Hard | NO | Provider adapter interface must be stable before dependent work can be certified.
P02-02 | P02 | P00-04,P02-01 | Governance | NO | Entitlement/licensing model must be stable before dependent work can be certified.
P02-03 | P02 | P02-01 | Soft | NO | Provider selection criteria must be stable before dependent work can be certified. (D98 note: NSE authoritative for exchange/EOD; low-cost yfinance candidate for single-user 15m runtime).
P03-01 | P03 | P02-01 | Hard | NO | Credential/secrets handling must be stable before dependent work can be certified.
P03-02 | P03 | P01-05,P03-01 | Hard | NO | Tenant/access controls must be stable before dependent work can be certified.
P04-01 | P04 | P01,P02,P03 | Hard | YES | Instrument master must be stable before dependent work can be certified.
P04-02 | P04 | P04-01 | Hard | YES | Provider symbol mappings must be stable before dependent work can be certified.
P04-03 | P04 | P04-01 | Hard | YES | Lifecycle/reference metadata must be stable before dependent work can be certified.
P05-01 | P05 | P02-01,P04-01 | Hard | YES | Local deterministic market feed must be stable before dependent work can be certified.
P05-02 | P05 | P02-01,P02-02,P03-01,P04-02 | Hard | YES | LIVE market adapter must be stable before dependent work can be certified.
P05-03 | P05 | P05-01,P04-02 | Hard | YES | Historical market adapter must be stable before dependent work can be certified. (D98 note: 10-yr history is a downstream data-activation dependency, not a development blocker; one-time baseline + monthly incremental EOD refresh).
P05-04 | P05 | P05-01,P05-02 | Hard | YES | Ingestion orchestration must be stable before dependent work can be certified.
P06-01 | P06 | P01,P04,P05 | Hard | YES | Normalization pipeline must be stable before dependent work can be certified.
P06-02 | P06 | P05-04,P06-01 | Hard | YES | Raw/canonical separation must be stable before dependent work can be certified.
P06-03 | P06 | P06-01,P06-02 | Hard | YES | Deduplication/idempotency must be stable before dependent work can be certified.
P07-01 | P07 | P06-01 | Hard | YES | Quality rule framework must be stable before dependent work can be certified.
P07-02 | P07 | P01-02,P07-01 | Hard | YES | Freshness/staleness must be stable before dependent work can be certified.
P07-03 | P07 | P02-03,P07-01 | Hard | YES | Provider reconciliation must be stable before dependent work can be certified.
P07-04 | P07 | P07-01,P07-02 | Hard | YES | Degraded-state contract must be stable before dependent work can be certified.
P08-01 | P08 | P01-02,P06-01 | Hard | YES | PIT storage model must be stable before dependent work can be certified.
P08-02 | P08 | P04-03,P05,P06 | Hard | YES | Corporate action ingestion must be stable before dependent work can be certified.
P08-03 | P08 | P08-02,P07-03 | Hard | YES | Adjustment/reconciliation must be stable before dependent work can be certified.
P09-01 | P09 | P04,P06,P08 | Hard | NO | Financial statement ingestion must be stable before dependent work can be certified.
P09-02 | P09 | P09-01,P01-03 | Hard | NO | Fundamental normalization must be stable before dependent work can be certified.
P09-03 | P09 | P09-02,P08-01 | Hard | NO | Valuation inputs must be stable before dependent work can be certified.
P10-01 | P10 | P02,P04,P06,P07 | Hard | NO | News/events ingestion must be stable before dependent work can be certified.
P10-02 | P10 | P08-01,P09-02 | Hard | NO | Estimates/consensus must be stable before dependent work can be certified.
P10-03 | P10 | P08-01,P07-01 | Required by applicability | NO | Macro datasets must be stable before dependent work can be certified.
P10-04 | P10 | P00-04,P01-05,P07-01 | Governance | NO | Alternative data governance must be stable before dependent work can be certified.
P11-01 | P11 | P06–P10 | Hard | YES | Engine input adapters must be stable before dependent work can be certified.
P11-02 | P11 | P07,P08,P11-01 | Hard | YES | Recalculation orchestration must be stable before dependent work can be certified.
P11-03 | P11 | P01-05,P11-01 | Hard | YES | Evidence lineage must be stable before dependent work can be certified.
P12-01 | P12 | P06–P11 | Hard | YES | Canonical data APIs must be stable before dependent work can be certified.
P12-02 | P12 | P11-03,P12-01 | Hard | YES | G2 DTO integration must be stable before dependent work can be certified.
P12-03 | P12 | P01-04,P07-02,P12-01 | Hard | YES | Live/snapshot/PIT API semantics must be stable before dependent work can be certified.
P13-01 | P13 | P07-04,P12-03 | Hard | YES | Global data-state framework must be stable before dependent work can be certified.
P13-02 | P13 | P09,P10,P12 | Hard | YES | Company data integration must be stable before dependent work can be certified.
P13-03 | P13 | P08,P11,P12 | Hard | YES | Portfolio integration must be stable before dependent work can be certified.
P13-04 | P13 | P09,P10,P11,P12 | Hard | YES | Research integration must be stable before dependent work can be certified.
P13-05 | P13 | P04,P11,P12 | Hard | YES | Screener integration must be stable before dependent work can be certified.
P13-06 | P13 | P11,P12 | Hard | YES | Decision integration must be stable before dependent work can be certified.
P13-07 | P13 | P07,P11,P12 | Hard | YES | Watchlist integration must be stable before dependent work can be certified.
P13-08 | P13 | P11,P12 | Hard | YES | Report integration must be stable before dependent work can be certified.
P13-09 | P13 | P10,P11,P12 | Hard | YES | Alert integration must be stable before dependent work can be certified.
P13-10 | P13 | P03,P12 | Hard | YES | Collaboration integration must be stable before dependent work can be certified.
P13-11 | P13 | P03,P12 | Hard | YES | Admin integration must be stable before dependent work can be certified.
P13-12 | P13 | P03,P12 | Hard | YES | Settings integration must be stable before dependent work can be certified.
P13-13 | P13 | P10,P12 | Hard | YES | Search integration must be stable before dependent work can be certified.
P13-14 | P13 | P03,P12 | Hard | YES | Action integration must be stable before dependent work can be certified.
P13-15 | P13 | P11,P12,P13-02..P13-09 | Hard | YES | Dashboard aggregation must be stable before dependent work can be certified.

## UI Coverage
UI ID | Surface | Scope Type | Market-Data Applicable | Primary Phases | Required Behavior / Scope
UI01 | Dashboard | Aggregation / presentation | Yes | P13,P14,P15 | Must consume governed domain outputs; no invented business logic
UI02 | Company Workspace | Data + analytics | Yes | P13,P14,P15 | Overview, financials, valuation, scorecard, risks, news, notes, evidence
UI03 | Portfolio | Data + analytics | Yes | P13,P14,P15 | Holdings, allocation, performance, risk, transactions, analytics
UI04 | Research | Data + intelligence | Yes | P13,P14,P15 | Research library, search, taxonomy, company/sector/macro research
UI05 | Screener | Data + filtering | Yes | P13,P14,P15 | Universe, filters, scores, sortable results, saved screens
UI06 | Decision Center | Governed workflow | Yes | P13,P14,P15 | Decisions, proposals, approvals, history, evidence
UI07 | Watchlists | Data + triggers | Yes | P13,P14,P15 | Persistent lists, triggers, score changes
UI08 | Reports | Data + provenance | Yes | P13,P14,P15 | Templates, generated reports, source/timestamp/lineage
UI09 | Alerts | Events + notification | Yes | P10,P13,P14,P15 | Rules, events, notifications, acknowledgement
UI10 | Collaboration | Contextual collaboration | Applicable | P13,P14,P15 | Comments, mentions, shared research/watchlists, assignments, activity
UI11 | Administration | Governed platform baseline | Applicable | P03,P13,P15 | Provider/admin configuration only where authorized
UI12 | Settings | Identity/preferences/configuration | Applicable | P03,P13,P15 | Data preferences and user configuration only where applicable
UI13 | Global Search | Cross-domain search | Yes | P10,P13,P14,P15 | Search company, research, holdings, decisions, evidence, alerts, reports
UI14 | Command Palette / Quick Actions | Action orchestration | Applicable | P13,P14,P15 | Open/create/review actions against governed domains

## Data Domains
Domain ID | Data Domain | Operating Mode | Requirement | Primary Phases | Primary Consumers
D01 | Market prices / quotes | LIVE + historical | Required | P05–P08 | UI, engines, portfolio, dashboard
D02 | Historical OHLCV | Historical / PIT | Required | P05–P08 | Charts, research, screening, engines
D03 | Fundamentals / financial statements | PIT + snapshot | Required | P09 | Company, research, scoring
D04 | Corporate actions | PIT + effective-date | Required | P08 | Portfolio, price adjustment, evidence
D05 | Instrument / security master | Current + historical lifecycle | Required | P04 | All domains
D06 | News / events | LIVE + historical | Required | P10 | Research, alerts, dashboard
D07 | Analyst estimates / consensus | Snapshot + PIT | Required | P10 | Research, valuation, dashboard
D08 | Macroeconomic data | Snapshot + historical/PIT | Required | P10 | Research, thematic analysis
D09 | Alternative data | Governed/approved only | Required by applicability | P10 | Research/engines where approved
D10 | Exchange/reference metadata | Current + historical where relevant | Required | P04–P05 | Security master, data quality

## Phase Gates
Phase | Gate | Gate Intent | Minimum Evidence | Promotion Rule
P00 | Scope/authority baseline | Establish scope, baseline, contracts, ownership, certification model and non-goals before implementation. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P01 | Canonical contract gate | Define canonical schemas, identifiers, timestamps, units, currencies, source/provenance and operating modes. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P02 | Provider abstraction/entitlement gate | Create provider-neutral adapter contracts and explicit licensing/entitlement boundaries. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P03 | Security gate | Secure provider credentials, service identities, tenant isolation and access controls. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P04 | Identity/master gate | Establish authoritative instrument identity, mappings, listings, exchanges, currencies and lifecycle state. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P05 | Acquisition gate | Implement deterministic/local ingestion first, then provider adapters for quotes, prices and historical market data. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P06 | Canonical pipeline gate | Normalize provider-specific payloads into governed canonical representations without feeding raw provider data directly to engines. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P07 | Data quality gate | Detect missing, stale, malformed, contradictory and out-of-order data; expose quality state and reconciliation evidence. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P08 | Historical/PIT gate | Support historical and PIT semantics, adjusted/unadjusted series, effective dates and corporate-action lineage. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P09 | Fundamentals gate | Ingest and normalize financial statements, ratios, valuation inputs and related fundamental datasets. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P10 | Intelligence data gate | Establish governed ingestion for news/events, consensus estimates, macro and approved alternative datasets. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P11 | Engine/evidence gate | Connect canonical data to existing engines and research flows with provenance, reproducibility and evidence lineage. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P12 | API/G2 gate | Expose governed data through stable APIs/contracts with live, snapshot and PIT semantics. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P13 | UI integration gate | Make all applicable existing UI surfaces consume governed data; retain non-data surfaces as baseline where applicable. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P14 | UX/visual/browser gate | Harden UX and qualify against the supplied screenshot target, including browser/visual validation where environment permits. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P15 | Full E2E certification gate | Certify provider-to-UI data lineage, engine outputs, evidence, degraded states and screenshot functional parity. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P16 | Production activation authority gate | Complete licensing, credentials, production connectivity, entitlement validation and controlled activation. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion
P17 | Operational/release certification gate | Operationalize monitoring, incident handling, provider failover/staleness controls, release evidence and production certification. | Phase-specific tests + artifacts + lineage/evidence + concessions where applicable | Explicit gate acceptance; no automatic promotion

## Status Legend
Status | Meaning
NOT STARTED | Planned but not begun
DISCOVERY | Read-only discovery / contract definition
IN DEVELOPMENT | Implementation underway
VALIDATION | Implementation complete; validation underway
CERTIFIED | Phase/work item accepted under its authority
CERTIFIED WITH CONCESSION | Accepted with explicitly recorded limitation
BLOCKED | Cannot proceed due to dependency/authority/environment
DEFERRED | Explicitly deferred by authority
CLOSED | Completed and closed; no further work without successor authority

## Parallel Execution
Wave | Primary Phases | Parallel Workstreams | Can Run in Parallel | Gate / Constraint
W0 | P00 | WS-A Governance & Contracts | P00 only | Establish baseline/governance first.
W1 | P01 + P02 + P03 | WS-A Governance & Contracts | P02/P03 discovery and prep may overlap P01; certification remains dependency-controlled. | P01 contract baseline must govern implementation.
W2 | P04 | WS-B Data Foundation | P04 work items can parallelize internally by security-master concerns. | Requires certified contract/security foundation.
W3 | P05 | WS-B Data Foundation | Acquisition/provider adapter work can split by domain/provider abstraction. | Requires instrument/master prerequisites.
W4 | P06 | WS-B Data Foundation | Normalization components can split by domain using P05 fixtures where available. | Phase gate follows P05.
W5 | P07 | WS-B Data Foundation | Quality rules, freshness, reconciliation and anomaly controls can split by domain. | Canonical pipeline must be available.
W6 | P08 | WS-B Data Foundation | Historical/PIT and corporate-action components can run in parallel by concern. | Depends on quality + canonical identity.
W7 | P09 + P10 | WS-C Intelligence Domains | Fundamentals and news/events/estimates/macro/alternative data can run in parallel. | Both consume the certified canonical foundation.
W8 | P11 | WS-D Engine / Research / Evidence | Engine/research/evidence integration can split by consuming domain. | Requires P09/P10 outputs.
W9 | P12 | WS-D Engine / Research / Evidence | API/G2 contracts can be developed per domain/resource. | Requires governed engine/research/evidence outputs.
W10 | P13 | WS-E Product UI | Most UI surfaces can run in parallel by surface; Dashboard intentionally follows underlying surfaces. | Shared product contracts/state first.
W11 | P14 | WS-E Product UI | Accessibility, responsive and visual-parity preparation can overlap. | Browser/functional qualification remains prerequisite-controlled.
W12 | P15 | WS-F Certification | Lineage, LIVE, SNAPSHOT/PIT, DQ propagation and security suites can run as parallel certification streams. | Final certification is one gate.
W13 | P16 | WS-F Production Onboarding | Licensing/provider onboarding preparation may be prepared, but activation remains a separate gated decision. | Production activation is NOT implied by development certification.
W14 | P17 | WS-F Operations & Release | Operational monitoring, runbooks and release certification can split by operational concern. | Requires authorized production activation path.

## Git & Workspace
Item | Decision | Value / Rationale
Decision | Use a NEW dedicated repository | iips-production-market-data
Windows folder | G:\IIPS-Production-Market-Data | Dedicated sibling workspace; do not nest under the existing E2E repository.
Initial branch | main | Use feature branches for implementation; protect main when repo governance is established.
First commit | Program baseline | Commit the spec/tracker/README/governance skeleton before implementation.
Relationship to existing IIPS repo | Separate | Integrate through stable contracts/APIs; do not merge the data-plane repository into the E2E repo.